**Project Status Report I**

| Date of Report Issue/Prepared: February 5, 2023 |
| --- |

Report Prepared By: Kym Gripal, Arshpreet Kaur

Employer/Organization: GoodApps

| Project Name:  Project Team:  Period Reporting:  Overall Project Health | CB Orders | |
| --- | --- | --- |
| GoodApps | |
| Start Date: **Jan 6, 2023** | End Date: **March 31, 2023** |
| Green (Good) - Yellow (Warning) - Red (Bad) | |

**Summary**

| **Project Status Summary** |
| --- |
| **Backend**  -Project is started for development from the backend -MongoDB models created and are being updated  -Database created and tested  -MongoDB routes are under creation  -API integration started to develop |

| **Accomplishments As Planned** | **Planned but not Accomplished** |
| --- | --- |
| **Database established** | Fully functional API, Client Pages |

Upcoming Objectives for **Feb 06, 2023 to Feb 24, 2023,**

| **Planned Activities/Tasks for Next Period** | | | | |
| --- | --- | --- | --- | --- |
| Activity/Task | Assigned To | | Duration | Date |
| Login Page | Kym Gripal | | 2 days | Feb 7, 2023 |
| Client Homepage | Mustafa Izici | | 10 days | Feb 17, 2023 |
| Products Page | Reyansh Srivastava | | 15 days | Feb 22, 2023 |
| Orders Page | Omar Nabi | | 15 days | Feb 22, 2023 |
| Search Page | Arshpreet Kaur | | 15 days | Feb 22, 2023 |

| **Milestones for Next Period** | | | |
| --- | --- | --- | --- |
| Milestone (Objective) | | Assigned To | Delivery Date |
| Fully functional API on remote server | | Kym Gripal | February 17, 2023 |
| Fully Functional Client-side page | | Mustafa Izici  Reyansh Srivastava  Omar Nabi  Arshpreet Kaur  Kym Gripal | February 22, 2023 |

**Managing Issues and Risk**

| **Issues/Problems** | **Resolution Strategy** | **Due Date** |
| --- | --- | --- |
| Backend and API needs improvement | Intensive research and brainstorming, intensive testing | Feb 23, 2023 |

| **Upcoming Risks** | **Risk Ranking**  **(Hi, Med, Low)** | **Risk Impact**  **(Hi, Med, Low)** | **Mitigation Strategy** |
| --- | --- | --- | --- |
| Lack of remote server experience, | Medium | High | Doing research, reading articles |